## Sheet1
Actitivy | Date | Description | Deliverables
User research (UX Design) | Days 1-7 | To determine the target market for Rugged Chairs and their needs. Samamtha will provide our team with all information concerning all the orders made; delivered or outsatanding. We will do research using this and more data from market | UX Report - A description of major characteristics of RC's type of user. Also, key requirements for that must be incorporated into the website to make the user experience optimized
Design the Website | Days 7-10 | Using the above data I will design a website for Rugged Chairs. This will be presented to Samantha for review and comments. Relevant changes will be incoporated in the design until the client is satisfied | Initial draft design using Photoshop
Create the website | Days 10-24 | After getting the go ahead from the client I will procedd with the creation of the website. The client wiill be informed of the progress at te end of each week | Working prototype of the website where client's inputs will be added where agreed upon
User Test the website | Days 25-26 | We will conduct a test of the workings of the website on 3 potential users. This will help us determine where improvenets are needed to create the ultimate user experience | Report on the good, the bad and ugly for our website; these are shared with the client for additional input
Update and finalize the Website | Days 27-30 | Updates will be made to the website using the report created after the user testing | Final version of the working website is presented to the client
Purpose | Amount | Notes
Deposit (for inititlization of project) | $1,500 | This needs to be paid when contract has been signed
UX, Designing and Creating Website | $1,500 | Paid after completion
TOTAL | $3000